## Day-by-Day Calendar
Week | Day / Date | Morning (Planning Sheet rows) | Afternoon (Planning Sheet rows) | ai Block (AI Literacy Track) | Journey lessons to assign / unlock | AOT lesson opportunity | Changes needed
W1 | Mon Jun 29 | Ice Breaker & Orientation · Journey Onboarding · Onboarding Survey | Incubator Community Norm Setting · Entrepreneurship Introduction · Close Out |  | 1.1 Journey Platform Onboarding · 1.2 Onboarding Survey · 1.3 Onboarding Challenges · 1.4 Orientation · 1.5 Entrepreneurial Mindset
W1 | Tue Jun 30 | Entrepreneurship as Problem Solving & Survey · Team Announcement · Your Entrepreneurial Profile · Startup Team Announcement | Startup Team Profiles & Get to Know · Team Agreements · Tech for Entrepreneurship · AI Introduction Block (90) · Close Out | Block 1: The Inheritance (90) | 1.6 Entrepreneurial Problem Solving · 1.7 Your Entrepreneurial Profile · 2.1 Teams & Tracks · NEW: Team Agreements lesson · NEW: AI-B1 lesson | AOT foundations milestones run inside the B1 history wall (10-35 segment) | Add Team Agreements lesson to CP2 · Add AI-B1 · Retitle 1.8 and 1.9 to venture language
W1 | Wed Jul 1 | Social Innovation Challenge Intro & Prep · Social Innovation Challenge | AI Tools for Pitch & Prototype Creation (80) · Pitch Prep · Startup Team Pitches · Judging & Awarding · Close Out | Block 2: Same Question, Different Mouths (80) | 2.10 Innovation Challenge (must be reachable today) · NEW: AI-B2 lesson | AOT Gen AI guidelines assignment = the cheat sheet fold-in (62-77 segment) | MOVE 2.10 to position 2.2 so it unlocks before today
W1 | Thu Jul 2 | Problem Analysis Introduction · Problem Statement & Vision Board | Stakeholder & Systems Analysis · Guest Speaker Block · AI Learning Block (60) · Close Out | Block 3: The Sanity Report (60) · Issue Find Your User pre-work (due Jul 6) | 2.4 Problem Statement · 2.5 Stakeholder Mapping · 1.12 Telling Fact from Fictions Online as B3 pre-read · NEW: AI-B3 · NEW: Find Your User challenge | Candidate slot for AOT lesson content (confirm L-numbers with D-Cal) | Assign 1.12 as B3 pre-read · Create Find Your User challenge, opens today, due Mon Jul 6
W1 | Fri Jul 3 | JULY 4TH HOLIDAY (no program) | Find Your User pre-work runs over the long weekend
W2 | Mon Jul 6 | User Analysis · Intro to Design Thinking | Empathy Intro & Exercises · AI Learning Block (90) · Close Out | Block 4: The Statistical Shadow (90) · Find Your User due | 2.6 Who is your Customer? · 2.3 Design Thinking · 5.1 Empathy Mapping · 5.7 Data Analysis and Data Visualization as B4 support · NEW: AI-B4 |  | Dedupe 2.3 vs 4.1 Human-Centered Design (keep 2.3, fold 4.1 in) · Pull 5.1 and 5.7 forward from CP5, needed today
W2 | Tue Jul 7 | Customer Discovery Intro · Customer Question Drafting | Project Management Skills · Fieldwork Prep / Outreach · AI Learning Block (90) · Close Out | Block 5: The Yes-Man (90) | 2.8 Customer Discovery (Secondary Sources) · 2.9 Customer Discovery (Primary Sources) · 4.2 Fieldwork Preparation · NEW: AI-B5 | Emerging risks content lands here: prompt injection + ai poisoning (D-Cal L7 note), 55-70 segment | Fix 4.2 spelling ("Prepration") · Pull 4.2 forward from CP4
W2 | Wed Jul 8 | Design Challenge DT Refresher · Define: Creating How Might Wes | Interview / Community Engagement Work Time · AI Learning Block (90) · Close Out | Block 6: The Generation Game (90, interview synthesis) | 2.7 How Might We? · 5.2 Define · 4.3 Empathy Research Challenge · NEW: AI-B6 |  | 5.2 overlaps 2.7, keep one · Pull 4.3 forward, it is the fieldwork itself
W2 | Thu Jul 9 | Refining your HMW / Ideation Prep · Ideation Brainstorm | Mentorship or Site Visit (180) |  | 3.9 How to Find and Keep a Mentor (assign before first site visit) |  | Unlock 3.9 ahead of today
W2 | Fri Jul 10 | Guest Speaker & Activities Block | Lightning Demo · AI Learning Block (90) · Close Out | Block 7: The Stage Set (90) | 3.10 How to Give and Receive Feedback (demo day) · NEW: AI-B7 | Candidate slot for AOT lesson content | Unlock 3.10 today
W3 | Mon Jul 13 | Analysis + Round 2 Ideation + Community Ideas Sourcing · Competitive Analysis | Solution Definition: First Sketch · AI Learning Block (90) · Close Out | Block 8: Not the Writer, Not the Designer (90) | 8.1 Market & Competitive Analysis (first touch) · NEW: AI-B8 |  | Pull 8.1 ahead of CP7 or dual-unlock, the sheet teaches competitive analysis today
W3 | Tue Jul 14 | Team Solutionizing · Final Team Solution Definition | Reflection & Mid Course Check In · Complete Midway Survey · AI Learning Block (90) · Close Out | Block 9: The Imaginary Friend (90) | NEW: AI-B9 · Midway Survey lives on platform
W3 | Wed Jul 15 | Prototyping Introduction & Challenge · Traction & Testing Introduction · Build & Outreach Worktime | Business Modeling · AI Learning Block (90) · Close Out | Block 10: The Footnote (90) | 6.1 Prototype (merge with 5.3) · 5.4 Traction (Customer Validation) · 6.2 The Lean Startup & MVPs · 6.3 Business Model Creation · 6.4 Testing · NEW: AI-B10 |  | Merge 5.3 + 6.1 into one prototype lesson · 2.2 Lean Startup (BMC) stays as W1 primer, 6.3 is the full treatment
W3 | Thu Jul 16 | Business Model Assumptions & Testing · Lean Startup & Testing Introduction | Mentorship or Site Visit (180) |  | 6.4 Testing continues
W3 | Fri Jul 17 | Guest Speaker & Activities Block | MVP Creation & Work Time · Make a Strategy for Weekend Outreach · AI Learning Block (90) · Close Out | Block 11: The Stack (90) | 1.10 Your First MVP (moved here from CP1) · NEW: AI-B11 |  | Move 1.10 from CP1 to CP6, MVP is a W3 concept
W4 | Mon Jul 20 | Project Management & Leadership Skills · Market & Industry Analysis · Competitive Analysis | Feedback Interpretation & Pivoting · MVP Build & Test Work Time · AI Learning Block (90) · Close Out | Block 12: The Invisible Market (90) | 8.1 Market & Competitive Analysis (full treatment) · NEW: AI-B12 |  | 8.1 sequence fix confirmed here, CP8 lesson taught before CP7 content
W4 | Tue Jul 21 | Costing your Startup · Revenue Models & Pricing | Startup Budgeting · Startup Accounting & Financials · AI Learning Block (90) · Close Out | Block 13: The Automated Self (90) | 7.1 Revenue Model and Pricing for your Startup · 4.7 Introduction to APIs as B13 pre-read · NEW: AI-B13 | AOT L7 AI agents content lands here (D-Cal: finish the agents section) | Keep 4.7 as the one retained coding lesson, it serves the coach build
W4 | Wed Jul 22 | Financial Projections & Break Even · Entrepreneurial Fundraising Introduction | Startup Communication Tools · AI Learning Block (90) · Close Out | Block 14: The Mark (90) | 7.2 Financial Strategy & Projections · 7.3 Entrepreneurial Fundraising · NEW: AI-B14
W4 | Thu Jul 23 | Pitch Introduction · Pitch Template Introduction | Mentorship or Site Visit (180) |  | 8.2 The Entrepreneurial Pitch
W4 | Fri Jul 24 | Guest Speaker & Activities Block | Project Management Review · Final Pitch Work Time (135) · Close Out | ai track complete, artifacts feed pitch work | 8.2 The Entrepreneurial Pitch continues
W5 | Mon Jul 27 | Prep for Semifinal Pitches | Commute to Pitch Venue · Semi Final Pitches |  | 8.4 The Final Pitch
W5 | Tue Jul 28 | Prep for Final Pitches | Commute to Pitch Venue · Final Pitches |  | 8.4 The Final Pitch
W5 | Wed Jul 29 | Final Survey & Reflections | Final Ceremony · Close Out |  | 8.3 Final Personal Reflection Challenge

## Journey Punch List
Journey lesson | Current position | Issue | Recommended action | Aligns to | Needed by | Priority
2.10 Innovation Challenge | CP2, last | Locked behind W2 customer discovery content; needed day 3 | Move to position 2.2, right after Teams & Tracks | Social Innovation Challenge, W1 D3 | Jul 1 | HIGH
8.1 Market & Competitive Analysis | CP8 | Sheet teaches market and competitive analysis before financials; CP8 unlocks after CP7 | Pull ahead of CP7 or dual-unlock | Competitive Analysis W3 D1, Market & Industry Analysis W4 D1 | Jul 13 | HIGH
5.7 Data Analysis and Data Visualization | CP5 | Needed as Block 4 support, locked deep in CP5 | Unlock for W2 D1 | ai Block 4 persona-vs-data chart | Jul 6 | HIGH
1.12 Telling Fact from Fictions Online | CP1 | Stray lesson; it is literally the Sanity Report theme | Assign as the Block 3 pre-read | ai Block 3 | Jul 2 | HIGH
NEW: Find Your User challenge | does not exist | Pre-work needs platform accountability over the long weekend | Create locked challenge: opens Jul 2, due Jul 6, submission = research + 2 conversation notes | D-Cal pre-work, feeds Block 4 | Jul 2 | HIGH
NEW: ai block lessons B1-B14 | do not exist | The afternoon track has no platform home | Add 14 lessons; completion = pod artifact link (matches the one-link-per-pod ops rule) | All ai days | Jun 30 | HIGH
NEW: Team Agreements | does not exist | Sheet teaches it Jun 30 with a signable artifact; no lesson | Add to CP2 after 2.1 | W1 D2 | Jun 30 | HIGH
4.8 How to Use Artificial Intelligence in Your App | CP4 | Predates the ai track; likely stale framing | Replace content with AOT Gen AI lesson or fold into B7 / B13 | AOT slot; ai Blocks 7 and 13 | Jul 10 | HIGH
5.1 Empathy Mapping · 5.2 Define | CP5 | Needed in W2, locked in CP5 | Pull both forward to W2 unlocks; 5.2 overlaps 2.7, keep one | Empathy W2 D1, Define W2 D3 | Jul 6 / Jul 8 | HIGH
1.10 Your First MVP | CP1 | MVP is a Week 3 concept on the sheet | Move to CP6 | MVP Creation, W3 D5 | Jul 17 | MED
1.8 What Makes An App Worth Building? | CP1 | App-track language; underlying lesson fits W1 problem solving | Retitle: What Makes a Venture Worth Building? | W1 frame | Jun 30 | MED
1.9 What Apps Do You Love? | CP1 | App-track language | Retitle to products/ventures, or retire | W1 frame | Jun 30 | LOW
2.5 Stakeholder Mapping / 3.11 Stakeholder Mapping | CP2 + CP3 | Duplicate lesson | Keep 2.5 (taught Jul 2); retire 3.11 or convert to applied follow-up | Stakeholder & Systems Analysis, W1 D4 | Jul 2 | MED
2.6 Who is your Customer? / 3.12 Who's Your Customer? | CP2 + CP3 | Duplicate lesson | Keep 2.6 (taught Jul 6); retire 3.12 | User Analysis, W2 D1 | Jul 6 | MED
2.3 Design Thinking / 4.1 Human-Centered Design | CP2 + CP4 | Overlapping content | Keep 2.3; fold 4.1 material in | Intro to Design Thinking, W2 D1 | Jul 6 | MED
5.3 Prototyping & Experimentation / 6.1 Prototype | CP5 + CP6 | Duplicate lesson | Merge into one prototype lesson | Prototyping, W3 D3 | Jul 15 | MED
2.2 Lean Startup (BMC) / 6.2 + 6.3 | CP2 + CP6 | BMC appears twice | Keep 2.2 as a W1 primer; 6.2 and 6.3 carry the full W3 treatment | Business Modeling, W3 D3 | Jul 15 | LOW
4.2 Fieldwork Prepration | CP4 | Typo in title; needed W2 D2 | Fix spelling; unlock Jul 7 | Fieldwork Prep / Outreach | Jul 7 | MED
4.3 Empathy Research Challenge | CP4 | It is the fieldwork itself, locked in CP4 | Unlock with interview work time | Interview / Community Engagement, W2 D3 | Jul 8 | MED
3.9 How to Find and Keep a Mentor | CP3 | Good content, wrong position | Unlock before the first site visit | Mentorship Thursday | Jul 9 | MED
3.10 How to Give and Receive Feedback | CP3 | Good content, wrong position | Unlock on Lightning Demo day | W2 D5 | Jul 10 | MED
4.7 Introduction to APIs | CP4 | Useful for the coach build | Keep; assign as Block 13 pre-read | ai Block 13 | Jul 21 | MED
3.1-3.8 Python series | CP3 | No planning sheet rows for coding; 2026 tech spine is the ai track | DECISION: optional self-paced enrichment, or retire for this cohort; keep 3.2 Replit if pods script the B13 coach | n/a | program decision | DECISION
4.4-4.6 HTML / CSS / Flask | CP4 | Same: no sheet rows | DECISION: optional enrichment or retire | n/a | program decision | DECISION
5.5 SQLite / 5.6 Numpy & Pandas | CP5 | No sheet rows; 5.6 supports stretch pods in B4 | Optional enrichment; 5.6 flagged for advanced pods | ai Block 4 stretch | Jul 6 | LOW

## Checkpoint-Week Map
Journey Checkpoint | Theme | Maps to program week(s) | Notes
CP1 Initiation | Onboarding, mindset, profile | W1 D1-D2 (Jun 29-30) | Order already matches Day 1-2. Retitle 1.8/1.9; move 1.10; 1.12 becomes B3 pre-read.
CP2 Teams & Tracks | Teams, problem, customer discovery | W1 D2-D4, spilling into W2 D2-D3 | Move 2.10 to 2.2. Add Team Agreements. 2.7-2.9 unlock in W2 with the days that teach them.
CP3 Discovery | Python series + mentor/feedback | W2 (3.9, 3.10 only) | Python 3.1-3.8 has no sheet rows: enrichment-or-retire decision. 3.11/3.12 are duplicates, retire.
CP4 | Fieldwork + web dev | W2 D2-D3 (4.1-4.3); B13 support (4.7) | 4.4-4.6 enrichment decision. 4.8 replaced with AOT Gen AI content or folded into B7/B13.
CP5 | Empathy, define, prototype, traction, data | W2 D1-D3 (5.1, 5.2) + W3 D3 (5.3, 5.4) + B4 support (5.7) | CP5 straddles two weeks: unlock lesson by lesson with the calendar, not as a unit.
CP6 Startup Experimentation | Prototype, lean startup, BMC, testing | W3 D3-D5 (Jul 15-17) | Merge 6.1 with 5.3. 1.10 Your First MVP moves here.
CP7 Startup Financials | Revenue, projections, fundraising | W4 D2-D3 (Jul 21-22) | Clean 1:1 with the sheet rows.
CP8 Final Launchpad | Market analysis, pitch, reflection, final | W3 D1 / W4 D1 (8.1, pulled forward) + W4 D4 through W5 | 8.1 is the one out-of-order lesson. 8.2 unlocks Jul 23, 8.4 pitch week, 8.3 debrief day Jul 29.
ai track (new lessons) | Blocks 1-14 + Find Your User | Every ai day, Jun 30 to Jul 22 | One lesson per block. Completion = pod artifact link. Recall openers live in the lesson body.